## Sheet1
Task name |  | Person | Start date | Finish date | Duration days | Status | Comment
Sprint 1 | Design Use Case Diagram for User's account & Website Category: - CRUD family tree info - Add a member's info to the family tree - Delete a member's info from the family tree | Nguyen | 2020-06-04 | 15/4/2020 | 9 | Done
| Interface UI UX | Hung | 22/4/2020 | 26/4/2020 | 4 | Done
Sprint 2 | Code Manage User Info: - CRUD user info | Hung | 2020-08-05 | 15/5/2020 | 7 | In Process
| Code Manage Family Tree: - CRUD book category - View family trees in detail | Hung | 21/5/2020 | 26/5/2020 | 11 | In Process
| Code Manage Member: - CRUD member info - Zoom in/out | Hung | 27/5/2020 | 30/5/2020 | 11 | In Process
| Code Login/ Logout/ Regiser | Hung | 2020-01-06 | 2020-04-06 | 11 | In Process
Sprint 3 | Update Database: Book & Book Category | Nguyen | 2030-04-06 | 2030-04-06 | 1 | Back Log
| Update Database: Customer & Supplier | Nguyen | 2030-04-06 | 2030-04-06 | 1 | Back Log