## Product Backlog
PRODUCT BACKLOG
ID | As a… | I want to be able to… | So that… | Assignee | Priority | Sprint | Status
1 | Member | Create my account | I can start to create my family tree | Hưng | Must | 1 | Done
2 | Member | Login | I can start to create my family tree | Hưng | Must | 1 | Done
3 | Member | Logout | I can quit my account or use other account | Hưng | Hưng | 1 | Done
4 | Member | Change my password | I can keep Secure | Hưng | Must | 1 | Done
5 | Member | Update my user's name | I can renew my account | Hưng | Must | 1 | Done
6 | Member | Create my family tree | I can manage my family member info | Hưng | Must | 2 | Done
7 | Member | View my created family tree list | I can add, update or delete what I want | Nguyen | Must | 2 | Done
8 | Member | Add, update or delete family member's info | I can complete my family tree | Nguyen | Must | 2 | Done
9 | Member | Zoom in/zoom out | I can check all brands and persons in my family tree | Nguyen | Must | 2 | Done